## Backlog
Milestone | Task | Est Hours | Assigned | Date Done
Milestone 1 | Site Map | 1 | Richard | 2021-05-02
Milestone 1 | Documentation | 1 | Alex | 2021-05-02
Milestone 1 | Database Design | 2 | Alex | 2021-05-02
Milestone 1 | Open-Source License Portion | 2 | Nicholas
Milestone 1 | Setup Backlog | 2 | Richard | 2021-05-02
Milestone 2 | Main Application Module Front End |  | Misty
Milestone 2 | Main Application Module Back End |  | Misty
Milestone 2 | Registration Module Front End |  | Alex | 2021-05-07
Milestone 2 | Registration Module Back End |  | Alex | 2021-05-07
Milestone 2 | Login Module Front End |  | Richard | 2021-05-08
Milestone 2 | Login Module Back End |  | Richard | 2021-05-08
Milestone 2 | Update Documentation
Milestone 3 | Stylize front end from milestone 2 |  | Richard
Milestone 3 | Refactor Login to use SpringBeans, Core and Dependency Incjection |  | Alex
Milestone 3 | Refactor Registration to use SpringBeans, Core and Dependency Incjection |  | Alex
Milestone 3 | Add Product Module Front End |  | Alex
Milestone 3 | Add Product Module Back End |  | Alex
Milestone 3 | Update Documentation |  | Richard
Milestone 4 | Add stylization to milestone 3 pages and touch up issues in style |  | Richard | 2021-05-23
Milestone 4 | Refactor Login Module to use Spring JDBC |  | Alex | Milestone 2
Milestone 4 | Refactor Add Product Module to use Spring JDBC |  | Alex | Milestone 3
Milestone 4 | Refactor Registration Module to use Spring JDBC |  | Alex | Milestone 2
Milestone 4 | Update Documentation |  | Richard | 2021-05-23
Milestone 5 | Search and View Inventory Back End |  | Richard | 2021-05-30
Milestone 5 | Search and View Inventory Front End |  | Richard | 2021-05-30
Milestone 5 | Update Inventory Module Back End |  | Richard | 2021-05-30
Milestone 5 | Update Inventory Module Front End |  | Richard | 2021-05-30
Milestone 5 | Delete Inventory Back End |  | Richard | 2021-05-30
Milestone 5 | Delete Inventory Front End |  | Richard | 2021-05-30
Milestone 5 | Update Documentation |  | Richard | 2021-05-30
Milestone 5 | Create Maven POM file, demonstrate how to build the package |  | Alex | 2021-05-30
Milestone 6 | Identify and leverage one client side component from jQuery
Milestone 6 | Document Main application module
Milestone 6 | Document Registration Module
Milestone 6 | Document Login Module
Milestone 6 | Document Add Inventory Module
Milestone 6 | Document View / Search Inventory Module
Milestone 6 | Update Documentation
Milestone 6 | Document Update / Delete Inventory Module
Milestone 7 | Add Bootstrap Intergration Main Application
Milestone 7 | Add Bootstrap Intergration Login Module
Milestone 7 | Add Bootstrap Intergration Registration Module
Milestone 7 | Add Bootstrap Intergration Product Module
Milestone 7 | Update Documentation
Milestone 8 | Fix any bugs
Milestone 8 | Prepare JavaDoc for the application
Milestone 8 | Create Slideshow
Milestone 8 | Record Team Video via Discord
Milestone 8 | Edit Video
Milestone 8 | Update Documentation
Milestone 8 | Submit Video to Youtube